Firfield Primary School Pupil Premium Plan

2017/18

In the school’s 2017 – 2018 budget, the school has been allocated £39,280.00 for support for those pupils eligible to receive Pupil Premium.  Provision will also include non-eligible pupils. Before interventions and funding allocations were made, a range of guidance, research and support was taken from the EEF Toolkit and relevant consultants from the local authority.

| Desired Outcome | Area / Initiative | Evidence and Rationale for this choice? | Monitoring- How will we ensure that this is implemented well? | Staff lead | Summary and impact |
| --- | --- | --- | --- | --- | --- |
|  | MATHS |  |  |  | March midpoint Review |
| Children’s basic acquisition of number and the application of skills and fluency are developed to enable pupils to gain in confidence in their maths and lead to a greater enjoyment in maths as the barriers are removed. | To implement ‘Numbers Counts’ programmes across both key stage 1 and 2 to improve basic skills in maths and raise confidence - Delivery of programme Key Stage 1 8 hours a week; £4555.00 Key Stage 2 9 hours a week; £6514.00 To continue to develop application of maths through Maths Software - Renewal of My Maths subscription - Provide and support additional access to My Maths software - Maths of the Day resources for outdoor maths learning £500.00 annual subscription - 1xTAs – 1hr sessions per week x 38 weeks – £604.00 to provide after school maths club To introduce ‘Rockstar Maths’ for pupils to improve basic multiplication tables knowledge. School and home log ins. £100.00 Provide additional I Pad software to support learning through technology and additional study opportunities £500.00 | The impact of these interventions which were in introduced as part of the school’s offer in 2015 have continued to be demonstrated by significant improvements in the pupils confidence and general acquisition and application of skills in the sessions and in class. The programme lasts for 12 weeks and pupils have demonstrated improvements during this time up to 19 months in learning. The maths software and additional resources ensure that the pupils are learning maths and the application of their learning through wide and varied means, including the opportunity to continue this learning development at home with log in information and resources. The after school club also ensures pupils can receive 1-1 support in maths learning. | The pupils complete a baseline test- Sandwell Maths test before the programme and again at the end to track the impact of the intervention on pupil’s progress. This information is collated and monitored by the school’s SENCO/ Inclusion Manager. Class teachers, SLT and governors will monitor the effectiveness of the software in enhancing pupils learning through monitoring and progress activities across each term. | HLTA/TA implementing programmes SENCO to monitor and report back to SLT/ Governors | The maths interventions continue to build upon children’s confidence in maths skills and application and this in turn supports the work carried out in class. Evidence from assessments throughout the year indicate that children are continuing to make good progress on the intervention. Outcomes will be assessed by the SENCo at the end of the year in July. My Maths continues to be well utilised to support maths learning and development across the school and by children at home. This will continue to be run into next year as this is a valuable resource for maths development. Due to the restructuring of the TA workforce, the club for My Maths is not available at this time, but children can utilise the programme during school and at home. Rock Star Maths has been a tremendous success and this is really supporting children in recalling their multiplication facts quickly and accurately. The set of IPads purchased by the PTA for the school are an invaluable resource to enhance learning. These are incredibly well used across the whole school from Reception to Year 6. Additional Apps enable focused curriculum support where required. |
|  | LITERACY |  |  |  |  |
| Pupils will develop their dexterity and stability and increase their fine motor manipulation in order to write more clearly and form letters consistently leading to a higher quality of presentation skills and a greater enjoyment in writing. The development of inference skills in reading and widening reading activities and experiences for pupils will assist in removing barriers to reading comprehension and improve reading outcomes. | To develop pupils’ core strength and fine and gross motor skills for writing. Implementation of Physical Literacy sessions for pupils in Key Stages 1 and 2 5 hours a week of Physical Literacy sessions; £2963.00 To raise attainment and achievement in reading through developing inference Resourcing and delivery of reading inference interventions to improve attainment and progress in reading DCC training and resources £3017.00 | This programme has run for several years within the school and the benefits of these sessions for identified pupils have been seen through improved skills in handwriting as well as balance and core strength. The use of inference skills has been identified as an area for the school to develop to increase the outcomes for pupils by the time they leave the school. Specific training has taken place for all teachers, HLTAs and TAs and so sessions weekly are in place to assist in this vital aspect of reading. Additional reading and comprehension will also assist in widening pupils reading choices and experiences. | Class teachers collate tracking information on attainment and achievement each term One of our Year 6 teachers is leading the intervention with teaching assistants and support from the LA consultant for English. | Monitored by the SENCO/ Inclusion Manager and Literacy Co-ordinator These sessions will be monitored by the literacy co-ordinator and SENCO SENCo Inclusion Manager and reported to SLT/ Governors | Physical Literacy sessions continue to support children well who have needed this core strength and balance input. This has been very beneficial in supporting the Occupational Health targets for identified children and developed confidence and skills. This will continue in the next year. These skills are being embedded through regular class activities and children are using these skills in reading and writing activities with increasing impact and accuracy. These skills are being developed across the curriculum further and individual and small group intervention activities with support staff in school. Reading is an area of school development for 2017 – 2018 |
|  | PASTORAL |  |  |  |  |
| Pupils will be able to deal more effectively with emotional and social difficulties through the high quality support and intervention from well trained, experienced staff at Nurture Club / Star Club sessions Pupils will have enjoyed access to additional extra-curricular opportunities, widening their own experiences and interests beyond school and increase their range of skills and aspirations Pupils will develop positive experiences of lunchtimes and develop social skills to support them in more independent playtime activities Pupils will have the opportunity to participate in additional practical learning opportunities during the Easter holiday. This will further develop skills, application and confidence in small groups. Pupils will have the opportunity to widen experiences and skills in attending a range of clubs available to enhance and develop their interests. Pupils will enjoy taking the opportunity to learn an instrument in school and be able to access instruments for home 7use. This opportunity may encourage future music learning and widen opportunities for pupils. | To provide support for identified pupils to improve self-esteem and emotional well-being. - One to one sessions with specific children - KS1 Nurture session for 8 children - KS2 Nurture session for 8 children - Nurture drop in sessions run daily as required TA support x 39 weeks £9000.00 To increase cross curricular involvement and enjoyment for pupils by proving funding residential breaks, Trips, Activities, Uniform and Equipment - To provide funding to enable all eligible pupils to access all residential, trips and activities, including holiday clubs. - To assist parents of eligible pupils with the purchase of uniform and equipment as necessary £1000.00 in funding pot towards activities etc. Provide Lunchtime club for 30 minutes for children. This is based on health living- sports and social skills through team building and use of additional resources. £1350.00 Easter School opportunities. These are provided for additional learning in small groups with a teacher and HLTA for 3 days a week. £837.00 Additional Clubs provision These clubs will be based around reading and literacy, spelling and the wider opportunities for learning through healthy eating, physical exercise and eating. (4 evenings a week.) £2370 Music tuition for the year. To enable pupils to learn an instrument with the DCC Peripatetic music teachers to widen opportunities and experiences. This includes additional funding to purchase required instruments to attend music clubs / continue with instrumental learning £1550.00 | Our school ‘Star Club’ is a real strength of the school’s provision and has grown and developed over time to meet the needs of increasing numbers of pupils. The school’s Nurture Leader is fully trained and qualified in this area of school support as is the SENCO/Inclusion Manager in school. These sessions have provided support and guidance for pupils and families and the feedback from both pupils and parents has been incredibly positive. Pupils enjoy attending the sessions and these make a positive difference to the attitudes, behaviour and well-being of pupils as identified by teachers. Through discussions with pupils and regular questionnaires, often it is the wider curricular activities that pupils indicate that they would like to take part in, both inside school and outside of school. These opportunities are important to widen the experiences and aspirations of pupils and develop new skills and interests. The club has been introduced to support the emotional and social needs of identified pupils who may find lunchtimes challenging. This club encourages an active engagement in an activity to develop positive attitudes going back into class for the afternoon sessions. This initiative for our Year 6 pupils has proved to be extremely worthwhile and valuable to the pupils who have been identified to attend. Comments from the pupils themselves in the feedback forms completed and submitted demonstrate clearly that they value this opportunity to identify where they require additional practice / support and have found these sessions very useful in overcoming misconceptions or revising past learning. Additional clubs have been well attended in previous years and are offered to identified pupils. This has led to some pupils who had not previously attended any wider aspects of school life regularly going to the clubs offered and widening their experiences of school life, friendship groups and interests and experiences. The school staff are well aware of the many positive factors music learning has on pupils, both from an academic and a pastoral point of view. The school works closely with Derbyshire Music Partnership to develop these wider opportunities for pupils that also include practicing for performances to parents and to wider audiences. This has shown pupils develop in confidence, resilience and self-discipline. | Families can monitor the impact through parental drop in sessions and see the work that is carried out. The Nurture Leader and SENCO meet to discuss the pupils who are in need of the Nurture group and the Inclusion Manager/ SENCO regularly monitors the provision. As the PP Co-ordinator, the Headteacher and named Governor; Graham Robertson monitor the provision and funding allocation through curriculum committee meetings. (interviews with pupils) The PE co-ordinator and SENCO/Inclusion Manager will monitor these sessions through observation and discussions with pupils and staff. The Headteacher monitors the sessions and feedback from pupils and staff. Class teachers take part in the music lessons and the school’s music Co-ordinator links directly with the music teachers in school. | SENCO and Nurture club leader will monitor through Boxhill Profile and session observations. Parents/ Carers of pupils in attendance are also invited to join taster sessions and feedback given As the PP Co-ordinator, the Headteacher and named Governor; Graham Robertson monitor the provision and funding allocation through curriculum committee meetings. (interviews with pupils) PE Co-ordinator and SENCO Year 6 staff These clubs are monitored by members of the SLT during the performance management cycle of events across the school and adhoc drop in sessions Class teachers and Music Co-ordinator | This area of school work continues to be incredibly beneficial for the children who attend and overtime the numbers of children attending these sessions are growing. These sessions are extremely well planned and delivered by our Nurture Leader in school and address the needs of the children who attend superbly. Feedback from children and parents whose children attend are incredibly positive and this offer has become a vital part of the school’s work on a daily basis in relation to children’s positive mental health. Children and their families have been assisted when requested with financial support to enable children to take part in a wide range of activities that they may otherwise not be able to attend. These opportunities and experiences widen life experiences for children as well as being enjoyable. They provide children with opportunities which they may not have considered previously. Additional lunchtime activities, resources and clubs have been made available to identified children. These will be reviewed again in preparation for the following year ahead. Additional investigation into Forest School Educational activities is to be considered for 2018 – 2019. The Easter School run by Year 6 teachers was, again, as in previous years well attended. The evaluations and feedback from the children in attendance was excellent and this is now a permanent fixture to the school’s timetable. This helps to revise areas of specific needs on a 1-1 basis, and develop confidence and resilience. These activities have now been added to the menu of interventions / clubs in the school and identified children take part in a range of boosters to support their learning as well as additional clubs on offer from First Grade Sports. The funds utilised to support music tuition in Year 4 this year has enabled children to experience learning the skill of playing a musical instrument. Concerts for parents have been performed and a musical concert in the summer will take place at Friesland. |

| Desired Outcomes | Area / Initiative | Evidence and rationale for this choice? | Monitoring- How will we ensure that this is implemented well? | Staff lead | Summary and impact |
| --- | --- | --- | --- | --- | --- |
|  | SEND /Attendance |  |  |  |  |
| Interventions will be stringently quality assured and evidence of rapid progress for pupils identified for interventions will be documented. | Release time for SENCo/Inclusion Manager to; - Monitor impact of interventions and work with individual children Ensure SENCo has non-class release time each week to complete her management duties for pupil Premium and SEND pupils including those with lower attendance. ½ day will be Pupil Premium funded. £4432.00 | The funding for the SENCO’s non-contact time has enabled her to focus on the delivery and impact of interventions and to carefully track the progress and attendance of individual pupils. Support for Teaching Assistants in delivery and collation of evidence in files has been incredibly beneficial in evidencing progress of individual pupils and devising their ‘next steps’. TOTAL COSTING £39,292 | The SENCO will monitor through her planned timetable across each term and reported to SLT/ Governors | Headteacher/ SENCO and Assistant Headteachers | The SENCo has stringently monitored the quality of interventions across the year so far, reporting to both staff and governors on the impact of the various interventions to ensure impact and accountability. |